## Overview
Town of Manlius — Facility Cost-Benefit Analysis
Overview of the project, the options, and how to use this workbook
This workbook compares realistic ways of addressing three facility problems: an aging Town Hall, an undersized leased police building, and a court that lacks proper space and security. It is an internal planning tool to help Town leadership choose a direction and decide what professional work to commission next. The figures are planning-level estimates for comparison, not final budget numbers or a commitment to any option.
A companion Word document, "Manlius CBA Overview & Explanations," gives the fuller narrative, the reasoning behind each cost item, and the sources. This tab is a built-in summary so the key points travel with the workbook.
The tabs in this workbook
Comparison — the five options side by side. Costs are shown as negative numbers; benefits are positive.
Tax Levy Impact — the effect on the tax levy and a median home if an option is financed with debt.
Assumptions — the framing judgments and key inputs, including the benefit values referenced by the Benefits tab.
Parameters — every input value with its source.
Benefits — the monetized benefits and how they flow into each option.
Scenario A through E — the full 30-year cost detail for each option.
Glossary — plain-language definitions of the technical terms.
How to read the numbers
Thirty years, in today's dollars
Every option is measured over 30 years. Future costs are converted to today's dollars (discounted at 4%) so options that spend money in different years compare fairly. This is the Present Value (PV). Because these are costs, they appear as negative numbers.
Costs against benefits
Each option totals its construction or repair costs, yearly operating costs, and the cost of carrying risk. Benefits we could put a dollar value on (avoided risk, lower insurance, efficiency) are then subtracted. Hard-to-measure benefits like civic pride are described but not counted.
Why "doing the minimum" is not cheap
Doing the minimum delays the problem but does not remove it. Buildings keep aging and systems keep failing. The analysis treats the status quo as a real cost, including future repairs and the cost of eventually building anyway.
The five options
Scenario A — Do Minimum
Fix urgent problems, keep renting the police building, keep the existing Town Hall. Includes a schedule of future repairs (boiler, roof, HVAC, and so on) because keeping an old building running has predictable costs, plus an eventual deferred build.
Scenario B — Full Rebuild
One new ~50,000 sqft building for Town Hall, Police, and Court. Sell the old Town Hall and end the police lease. Built on the Trophy Point professional estimate; the most reliable of the five.
Scenario C — Split
Build a new Police/Court building and renovate and expand the Town Hall. The Town Hall work is about $10.5M because the VIP study found it needs an addition, not just a renovation.
Scenario D — Purchase
Buy and convert an existing building for Police and Court, and renovate and expand the Town Hall. Lowest-confidence option because no building has been identified yet.
Scenario E — Purchase + Do-Minimum Town Hall
Buy and convert a building for Police and Court (like D), but give the Town Hall only base repairs (like A). Solves the police problem at the lowest UPFRONT cost, but the Town Hall's accessibility and space problems remain — and the deferred Town Hall renovation in Year 30 makes E cost more than D over 30 years.
What this analysis can and cannot do
It can support a decision about direction and show what professional work to commission next. It cannot serve as a final budget and does not replace an engineering study, a bond-capacity opinion, an asbestos survey, or an appraisal.
Confidence by option: B is highest (professional estimate); C is good (VIP study plus cost rates); A is lower (Town estimates); D and E are lowest (no building identified, conversion cost uncertain).

## Comparison
Town of Manlius — 5-Scenario Comparison
Side-by-side summary. Scenarios B and C are anchored by Trophy Point and VIP engineering estimates. Scenarios D and E carry the highest cost uncertainty (no building identified yet). E defers the Town Hall renovation to Year 30; on a 30-year NPV basis Scenario D is lowest.
Metric | Scenario A | Scenario B | Scenario C | Scenario D | Scenario E | Notes
Description | Status quo + compliance | 50K sqft new combined facility | New PD/Court + renov+add TH | Purchase bldg + renov+add TH | Purchase bldg + do-min TH
CAPITAL COSTS
Total project cost | -1164739 | -47348603.3367 | -44483803.346 | -20802030 | -8127217.5 | S0 = Yr 1 remediation only
Amount to be bonded | 0 | 46848603.3367 | 43983803.346 | 20302030 | 7627217.5 | Net of grants
Annual debt service | 0 | 2876108.042 | 2700233.5504 | 1246372.9459 | 468246.6504 | 30-yr bond at 4.5%
30-YEAR FINANCIAL ANALYSIS (costs shown as negative)
30-yr Gross Cost (PV, cost only) | -23698512.4247 | -57814686.0196 | -54941593.0858 | -28128968.992 | -22490992.0942 | Discounted at 4%; before benefits
30-yr Benefits NPV | 0 | 6815497.0097 | 5154572.8947 | 5462103.2206 | 1878006.9065 | Tier 1+2 monetized
30-yr Net PV (cost after benefits) | -23698512.4247 | -50999189.0099 | -49787020.1911 | -22666865.7714 | -20612985.1877 | **KEY METRIC**
Differential vs. lowest | -3085527.237 | -30386203.8222 | -29174035.0034 | -2053880.5837 | 0 | $0 = lowest
COST PER RESIDENT
Town population | 32400 | 32400 | 32400 | 32400 | 32400
Net PV per resident (if financed w/ debt) | -731.4356 | -1574.049 | -1536.6364 | -699.5946 | -636.2032
Avg annual cost per resident (if financed w/ debt) | -24.3812 | -52.4683 | -51.2212 | -23.3198 | -21.2068
KEY DRIVERS / DECISION FACTORS
Solves the building problem | No — defers | Yes — fully | Yes — partial | Yes — partial | Yes — partial
Cost estimate basis | Estimates | Trophy Point (real) | VIP study + TP rates | Highest uncertainty | Highest uncertainty
Police properly sized | No (220 sqft/emp) | Yes (~425/emp) | Yes (~425/emp) | Depends on building | Depends on building
Town owns asset | No PD ownership | Yes (full) | Mixed | Mixed | Mixed
Lease dependency | Continues | Eliminated | Eliminated | Eliminated | Eliminated
Asbestos exposure | Continues | Eliminated | Continues in TH | Continues in TH | Continues in TH
Construction discovery risk | Low | Low (new site) | HIGH (TH renov) | VERY HIGH (TH + purchased bldg) | HIGH (purchased bldg)
Construction timeline | Year 1 | 2 yrs | 3 yrs (2+1) | 2 yrs (1+1) | 1–2 yrs
Future flexibility | Constrained | Designed for growth | Limited | Limited | Limited
Political case | Status quo | Transformational | Compromise | Pragmatic | Pragmatic / low-cost
Approval complexity | Town Board | Bond referendum | Bond referendum | Bond referendum | Bond referendum
Site identification needed | No | Yes | Yes | Yes — must find building | Yes — must find building
CRITICAL ASSUMPTIONS TO CONFIRM
Bond counsel memo on debt capacity ($35-47M range across scenarios)
Comprehensive asbestos survey on Town Hall — affects C, D (renovation) and E (base repairs)
Police chief confirms 20-yr growth (+7 placeholder)
Site identification for B and C; building identification for D and E
Conversation with Village re: Village Centre plans
Real grants pipeline (DASNY/NYSERDA/DCJS)
Insurance broker memo on premium impact
Town Hall demographic placeholders (population, assessed value, median home)
$125K Buildings Maintenance Contract line — recurring or one-time?

## Tax Levy Impact
Tax Levy Impact
Effect on the General Fund tax levy and on a median home IF a scenario is financed using debt (a 30-year bond). These figures assume the full bonded amount is raised through the property tax levy. Actual impact depends on grants, reserves, and the Town's final financing decision.
Metric | Scenario A | Scenario B | Scenario C | Scenario D | Scenario E
Current General Fund tax levy (2026) | 13330087 | 13330087 | 13330087 | 13330087 | 13330087 | Same for all (2026 budget)
Annual debt service (if bonded) | 0 | 2876108.042 | 2700233.5504 | 1246372.9459 | 468246.6504
% increase to GF levy | 0% | 21.58% | 20.26% | 9.35% | 3.513%
Total town TAXABLE value | 4800000000 | 4800000000 | 4800000000 | 4800000000 | 4800000000 | Town Assessor
Median home assessed value | 332100 | 332100 | 332100 | 332100 | 332100 | Town Assessor
Est. annual tax increase on median home | 0 | 198.9907 | 186.8224 | 86.2334 | 32.3968
Est. monthly increase on median home | 0 | 16.5826 | 15.5685 | 7.1861 | 2.6997
How to read this tab
• These numbers apply only if a scenario is financed with a 30-year bond (debt finance). Scenario A issues no debt, so its tax impact is $0.
• The annual tax increase on a median home = (annual debt service ÷ total taxable value) × median home assessed value.
• Taxable value ($4.8B) and median home ($332,100) are from the Town Assessor.
• This is the gross levy impact before any grants, reserves, or fund balance the Town might apply to reduce what must be bonded.
• How a bond interacts with the NYS property tax cap and the Town's debt limit must be confirmed by bond counsel and the financial advisor.

## Assumptions
CBA Assumptions
Part 1 lists the framing and strategic assumptions that shaped the analysis and conclusions. Part 2 lists the key numeric inputs (full detail on the Parameters tab).
PART 1 — FRAMING & STRATEGIC ASSUMPTIONS (the judgments behind the conclusions)
Column B = the assumption in brief. Column C = what it means and why it matters.
How the scenarios are compared
30-year horizon is the right basis | We compare all options over 30 years. A longer horizon would favor new construction more (assets last 50+ years); a shorter one would make 'do minimum' look better. 30 years is a standard municipal CBA window but it is a choice that affects the ranking.
Net present value, not upfront cost, is the deciding metric | We assume the right comparison is total discounted cost over 30 years — including operating, maintenance, and risk — not just the construction price tag. A cheaper building that costs more to run can be the worse choice.
The status quo is not free | We assume that doing nothing still carries real, accumulating costs: an aging building, a leased police facility, ongoing risk exposure, and eventual capital replacement. 'Do Minimum' is modeled as a real cost stream, not a zero baseline.
Doing minimum defers but does not avoid the build | We assume that at the end of 30 years the Town would still need to replace these facilities, so 'Do Minimum' includes the cost of building anyway at Year 30. This is the single biggest driver of that scenario's cost and reflects deferral, not avoidance. (Toggle in Parameters to test the strict 30-year-only view.)
The buildings and the need
The police facility is genuinely undersized | We assume 205 sqft/employee is an operational problem, not just tight quarters, and that the department needs ~425 sqft/employee to function and grow. This drives the size — and therefore cost — of every build scenario.
Renovation alone cannot fix the Town Hall | We accept the VIP study's professional conclusion that the existing footprint cannot accommodate an elevator plus current functions, so an addition is required, not optional. This is why the renovation scenarios cost ~$10.5M, not the ~$5M a cosmetic renovation would.
The existing Town Hall has resale value and can be sold | Scenario B assumes the Town Hall can be sold for ~$1M and returned to the tax roll. This assumes a willing buyer and that selling a former municipal building is politically and practically acceptable.
20-year growth to ~53 police employees | We assume modest police growth (+7 over 20 years). If the town grows faster or service demands rise, every build scenario is undersized; if it shrinks, they are oversized.
The police lease and the Village
The Town can exit the police lease cooperatively | We assume that when a new facility is ready, the Town can end the Village lease with normal notice and rent through the calendar year — i.e. the Village is a cooperative counterparty.
The Village does not force the Town's hand early | The lease auto-terminates if the Village sells the Village Centre. We assume this does not happen before the Town is ready. If it does, the Do Minimum timeline compresses and options narrow.
Financial feasibility
The Town can access bond financing at roughly current rates | We assume a 30-year bond near current AA municipal rates (~4.5%). The cost estimates are credible, but whether the Town can carry the resulting debt service against the existing levy and tax cap is unconfirmed — this is a top open question.
A project of this scale can win approval | We assume the larger build scenarios can secure the necessary board and likely voter (bond referendum) approval. This is a political assumption, not a financial one.
Benefits and the purchase scenarios (D and E)
Benefits actually land in the budget | We assume the avoided risks, insurance savings, and efficiency gains are activvly tracked and recorded, rather than being absorbed invisibly. If they aren't actively managed, the modeled benefits may appear to overstate the realized gain.
A suitable building exists to purchase (Scenarios D and E) | Scenarios D and E both assume a ~25,000 sqft building can be bought for around $1M and converted for police/court use. No specific building has been identified, so both are the least certain on the build side and their cost could change substantially once a real candidate is evaluated.
Scenario E leaves the Town Hall problem unsolved, by design | Scenario E has the lowest UPFRONT cost (~$8M) because it buys the police/court building (like D) but gives the Town Hall only base repairs instead of the full VIP renovation. However, like Scenario A, E does not solve the Town Hall — so the model charges E for that renovation as a DEFERRED build in Year 30 (the $10.5M VIP renovation+addition, escalated at construction inflation). On a 30-year NPV basis this makes E more expensive than D, which fixes the Town Hall up front. E trades a lower upfront cost for a larger deferred obligation and 30 more years of an unfixed Town Hall.
What we deliberately did NOT monetize
Civic and intangible value is acknowledged, not counted | We assume civic pride, public-meeting dignity, community presence, and long-term flexibility are real but should stay out of the NPV to keep it credible. They belong in the narrative, not the spreadsheet.
PART 2 — KEY NUMERIC INPUTS (reference; full detail on Parameters tab)
These are the headline numbers behind the scenarios. The Parameters tab holds the complete, sourced list.
Analysis
Horizon / discount rate | 30 years · 4.0% NPV discount
Inflation (general / construction / operating) | 2.5% / 4.0% / 3.0%
Bond | 4.5%, 30-year term (placeholder pending advisor)
Buildings & program
Town Hall existing size | 14,473 sqft (VIP measured)
Police building (leased) / employees | 9,441 sqft · 46 today, 53 future
Police standard used | 425 sqft/employee (mid of 350-500)
Post-renovation Town Hall (B/C/D) | 22,288 sqft (existing + 7,815 addition)
Headline costs by scenario
Scenario A — Do Minimum | ~$1.0M Year 1 remediation + future capital + deferred build
Scenario B — Full Rebuild | Trophy Point $39.6M construction; ~$47M all-in
Scenario C — Split | New PD/Court + VIP renovation+addition ($10.5M); ~$44M all-in
Scenario D — Purchase | $1M building + conversion + VIP renovation; ~$21M all-in
Scenario E — Purchase + Do-Minimum Town Hall | $1M building + conversion + base Town Hall repairs; ~$8M upfront (lowest upfront), but +$10.5M deferred Town Hall build in Yr 30
Key cost drivers
VIP renovation + addition (B/C/D Town Hall) | $10.5M (midpoint; excludes asbestos)
Asbestos abatement | $600K (estimate; needs survey)
Land (B 7 acres / C 4 acres) | $100K/acre → $750K / $450K
Estimated grants | $500K (placeholder)
Demographics (population / median home) | 32,400 / $270K
Confidence level of analysis by scenario
Scenario A — Do Minimum | LOW-MEDIUM — built on internal estimates; deferred build is a judgment
Scenario B — Full Rebuild | HIGH — anchored by Trophy Point engineering estimate
Scenario C — Split | MEDIUM-HIGH — VIP study + Trophy Point rates; asbestos is the wildcard
Scenario D — Purchase | LOW — no building identified; conversion cost highly variable
Scenario E — Purchase + Do-Minimum Town Hall | LOW — like D, no building identified and conversion cost variable; Town Hall left unaddressed adds long-term risk
BENEFIT INPUT VALUES (referenced by the Benefits tab)
These annual dollar values feed the Benefits tab by cell reference, so they are set in one place. Source/notes in the right column.
Avoided risk-weighted exposure | 170000 | Sum of risk exposures (security, PESH, records, cash, insurance pressure); see Cost of Inaction in Parameters. Refine w/ broker.
Insurance premium reduction | 65000 | ~12% premium reduction from modern facility. Refine w/ insurance broker.
Property tax recovery on sold TH | 20000 | Only Scenario B: sold Town Hall returns to tax roll.
Police-Court co-location efficiency | 20000 | Shared sallyport/transport savings when PD and Court share a building.
Staff productivity (workaround time) | 40000 | Recovered staff time from a functional building.
Recruitment/retention (police) | 30000 | Reduced turnover/recruiting cost with adequate facilities.
Health/wellness avoided costs | 10000 | Air quality, ergonomics, mold remediation avoided costs.
Single-building maint efficiency | 25000 | Only Scenario B: one building vs two (shared HVAC/roof/systems).

## Parameters
Town of Manlius — Town Hall / Police / Court CBA (v8)
Updated: VIP renovation study integrated, Town Hall sqft corrected, Scenarios D and E added
Blue=input. Yellow=TBD. Pink=Trophy Point. Light blue=VIP study. Purple=calculated.
Parameter | Value | Unit | Source / Notes
Analysis Assumptions
Analysis period | 30 | years | Standard
Analysis start year | 2027 | year | Bond 2026; construction 2026-2028
Discount rate (NPV) | 4% | % | Municipal cost-of-capital
General inflation | 0% | % | Set to zero for constant dollar analysis
Construction cost inflation | 0% | % | Diffrence from gen inflation
Operating cost inflation | 0% | % | Diffrence from gen inflation
Utility inflation | 0% | % | Diffrence from gen inflation
Bond rate | 4.5% | % | AA muni benchmark
Bond term | 30 | years | Standard
DEMOGRAPHIC / TAX BASE INPUTS
Town population | 32400 | residents | 2020 Census
Households | 14000 | households | Estimate; verify
Total town TAXABLE value | 4800000000 | $ | Town Assessor: taxable value after exemptions ($4.8B). Full assessment roll is $5,416,163,767; taxable base is used because the levy applies to taxable value.
Median home assessed value | 332100 | $ | Town Assessor: median assessed value of a home in the Town.
Current General Fund tax levy | 13330087 | $/yr | 2026 Budget A00.4.1001
Town tax rate per $1,000 | 2.7771 | $ | Calculated: GF levy / taxable value × 1,000.
Existing Buildings — Facts
Town Hall square footage | 14473 | sqft | Per VIP Building Conditions Assessment (Nov 2024): 7,418 lower + 7,055 floor 01
Town Hall employees | 22 | people | Mid of 20-25 per user
Asbestos confirmed? | Yes | Y/N | Churchill Environmental 2014-16
Town Hall sale value | 1000000 | $ | User estimate
Police building square footage | 9441 | sqft | Per 2023 lease
Police employees (current) | 46 | people | User-provided
Police 20-yr employee growth | 7 | people | Estimate
Police annual lease (2026) | 106203 | $/yr | 2026 Budget
Police lease escalator | 2% | % | Per 2023 lease
Termination | Auto if VC sold | text | Per lease clause
POLICE SPACE PROGRAM CALCULATOR
Industry benchmark — Mid sqft/emp | 425 | sqft/emp | Mid of 350-500 IACP range
Future employee count | 53
Required police sqft (mid) | 22525
Current sqft per employee | 205.2391 |  | vs. industry 350-500 — significantly undersized
Town Hall Operating Costs (annual)
Utilities | 24600 | $/yr | 8-yr avg National Grid
Buildings-Contractual recurring | 10000 | $/yr | 17-yr normalized avg
Cleaning | 17160 | $/yr | 2026 Budget
Landscaping | 7480 | $/yr | 2026 Budget
Snow removal | 3000 | $/yr | 2026 Budget
Water | 1300 | $/yr | 2026 Budget
Security | 1000 | $/yr | 2026 Budget
Pest control | 1000 | $/yr | 2026 Budget
Internet | 3000 | $/yr | 2026 Budget
Phone (bldg portion) | 8000 | $/yr | Estimate
Buildings personal services | 24960 | $/yr | 2026 Budget
Buildings Maintenance Contract (removed) | 0 | $/yr | Set to $0: the 2026 budget $125K line was not recurring Town Hall maintenance. Actual recurring building maintenance (~$9-10K/yr, per A00.5.1620.400 history) is already captured in the 'Buildings-Contractual recurring' line above.
Subtotal Town Hall operating | 101500
Police Building Operating Costs (annual)
Building maintenance | 5676 | $/yr | 10-yr avg
Cleaning supplies | 4000 | $/yr | 2026 Budget
Security | 360 | $/yr | 2026 Budget
Bldg maintenance line | 15000 | $/yr | 2026 Budget
Subtotal Police occupancy (lease + maint) | 131239
FUTURE CAPITAL REPLACEMENT — Town Hall (Scenario A)
Boiler replacement (Yr 5) | 300000 | $ today | Old boiler with 2018 issues
Roof replacement (Yr 8) | 400000 | $ today | 14K sqft × $30/sqft
Electrical service upgrade (Yr 10) | 200000 | $ today | Modernize for code
HVAC system overhaul (Yr 12) | 350000 | $ today | Beyond routine
Remaining window/envelope (Yr 15) | 250000 | $ today | Areas not covered 2015-16
Parking lot resurface (Yr 18) | 150000 | $ today | 20-yr life
Boiler replacement #2 (Yr 22) | 350000 | $ today | Second cycle
Roof replacement #2 (Yr 28) | 450000 | $ today | Second cycle
TROPHY POINT FEASIBILITY — Jul 2025 (Scenario B)
New building (50,000 GSF) | 32677719 | $ | TP: incl GC, OH, design contingency, escalation
Storage buildings | 625823 | $ | Trophy Point
Site work | 5268977 | $ | Trophy Point
FF&E allowance | 1000000 | $ | Trophy Point
ALT #1: Geothermal | 3716839 | $ | TP alternate
Include geothermal? (1/0) | 0 | 0/1 | Toggle
Trophy Point building sqft | 50000 | sqft | Per TP
VIP BUILDING CONDITIONS ASSESSMENT — Nov 2024
Renovation cost (low) | 4000000 | $ | VIP: existing 14,473 sqft renovation
Renovation cost (high) | 5000000 | $ | VIP
Renovation cost (used) | 4500000 | $ | VIP midpoint; used in Scenarios C and D
Addition cost (low) | 5000000 | $ | VIP: 7,815 sqft addition
Addition cost (high) | 7000000 | $ | VIP
Addition cost (used) | 6000000 | $ | VIP midpoint
VIP total (renov + addition) | 10500000 | $ | Sum of midpoints; includes 10% design + 20% construction contingency
Addition sqft | 7815 | sqft | Per VIP plans
Post-renovation total sqft | 22288 | sqft | Existing 14,473 + addition 7,815
Asbestos abatement (additional) | 600000 | $ | Not in VIP estimate; typical for confirmed-asbestos building
Soft Costs (EXCLUDED by Trophy Point and VIP)
A&E / Design fees | 7.5% | % | Typical 6-10%
Owner's contingency | 5% | % | On top of design contingency
Construction Manager/Owner's Rep fees | 3% | % | If using CM
Bond issuance costs | 1.5% | % | Applied to bond
Legal, advisory, permits | 200000 | $ | Lump
Asbestos abatement (Scen B site) | 0 | $ | Site-dependent
LAND ACQUISITION
Scenario B — Acres needed | 7 | acres | 50K sqft + parking + setbacks
Scenario C — Acres needed | 4 | acres | ~30K sqft PD/Court + parking
Estimated land cost per acre | 100000 | $/acre | CNY suburban commercial range
Closing costs, survey, Phase I | 50000 | $ lump | Legal, title, survey, ESA
Scenario B total land cost | 750000
Scenario C total land cost | 450000
Scenario C — New PD/Court Sizing
Police sqft (from calculator) | 22525
Court sqft | 4500 | sqft | Refine with Justice
Common/mechanical multiplier | 15% | % | Lobby/corridors/mech
Total PD+Court sqft | 31079
Effective $/sqft for C | 720 | $/sqft | TP avg + 10% standalone premium
Site work — C (new PD/Court) | 3700000 | $ | 70% of TP site
SCENARIO D & E — Purchase Building for PD/Court
Building purchase price | 1000000 | $ | User estimate; needs site identification
Building sqft (purchased) | 25000 | sqft | Assumed; refine after target identified
Conversion to police use $/sqft | 200 | $/sqft | Holding cells, sallyport, evidence, HVAC, electrical, ADA — high uncertainty
Site work / parking upgrades | 500000 | $ | Sallyport pad, parking expansion, security fencing
FF&E for converted building | 400000 | $ | Lower than new build but still substantial
Total purchased PD/Court cost (D & E) | 6900000
Cost of Inaction — Capital
Records room water/envelope | 90000 | $ | Mid $25-150K
Electrical/heater hazard | 30000 | $ | IMMEDIATE
Elevator (ADA) | 450000 | $ | Mid $300-600K
ADA doorknobs | 10000 | $ | Mid $5-15K
Building security | 30000 | $ | Mid $15-50K
Staff restroom access | 60000 | $ | Mid $25-100K
Police building compliance | 50000 | $ | Reduced; Village (landlord) responsible for most building compliance per lease — limited to tenant fit-out and PESH items
Asbestos overhead premium | 20% | % | On disturbance work
Cost of Inaction — Annual Risk
Security/workplace violence | 50000 | $/yr | Actuarial benchmark; refine w/ broker
Restroom Public Employee Safety and Health Bureau | 30000 | $/yr | Mid $10-50K
Cash transport courier | 15000 | $/yr | Mid $5-25K
Records loss/mold | 50000 | $/yr | Mid $25-100K
Insurance premium pressure | 25000 | $/yr | Refine w/ broker
Other Inputs
Two-building overhead (C/D) | 35000 | $/yr | Janitorial/HVAC/IT/grounds
Rec revenue (C/D) | 5000 | $/yr | Modest user estimate
Estimated grants | 500000 | $ | DASNY/NYSERDA/DCJS placeholder
Construction period — B (Full Rebuild) | 2 | years | Per Trophy Point
Construction period — C PD/Court | 2 | years | Per Trophy Point (2-yr build)
Renovation period — TH (C and D) | 1 | years | After PD/Court done
Conversion period — D and E | 1 | years | Existing building conversion
New building $/sqft/yr | 11 | $/sqft/yr | Modern muni $9-13
Renovated TH cost factor | 85% | % | 85% of pre-reno (efficiency)
Converted building $/sqft/yr | 9 | $/sqft/yr | Slightly lower than new-build benchmark
SCENARIO 0 — DEFERRED BUILD MODELING
Include deferred build? (1/0) | 1 | 0/1 | Recognizes S0 isn't a 30-yr solution
Year of deferred build | 30 | year | Last year of analysis
Deferred build cost (today's $) | 47348603.3367 |  | Linked to Scenario B; edit to override
SCENARIO E — DEFERRED TOWN HALL BUILD
Include deferred TH build? (1/0) | 1
Year of deferred TH build | 30
Deferred TH build cost (today's $) | 10500000

## Benefits
Monetized Benefits — Tier 1 + Tier 2
Annual benefit by category and scenario.
Benefits flow into Scenarios B, C, and D as negative cash outflow.
Benefit Category | Annual Value | Tier | Scen B | Scen C | Scen D | Scen E | Start Yr Offset | Inflation | Methodology | Source / Basis
TIER 1 — High-confidence quantification
Avoided risk-weighted exposure | 170000 | 1 | Y | Y | Y | N | 0 | general | Sum of cost-of-inaction recurring (security + restroom + cash + records + insurance) | Risk items built from Town walkthrough + NYS PESH (dol.ny.gov) and insurance exposure; refine with Town broker.
Insurance premium reduction | 65000 | 1 | Y | Y | Y | Y | 0 | general | ~12% of $542K Unallocated Insurance line | Property/liability insurance literature; Town's insurance line ($542K). Confirm % with Town broker.
Property tax recovery on sold TH | 20000 | 1 | Y | N | N | N | 0 | general | Only Scenario B sells TH; C and D keep it (renovate) | Town Assessor: returning sold Town Hall to the taxable roll (Scenario B only).
Police-Court co-location efficiency | 20000 | 1 | Y | Y | Y | Y | 0 | operating | Eliminated prisoner transport, shared sallyport | IACP Police Facilities Planning Guidelines (theiacp.org) — shared sallyport/transport efficiency.
TIER 2 — Defensible with methodology
Staff productivity (workaround time) | 40000 | 2 | Y | Y | Y | N | 0 | operating | 0.5 FTE equivalent across departments | U.S. EPA Office Building Occupant's Guide to IAQ; Harvard T.H. Chan School of Public Health (productivity/cognition); LBNL ventilation/absenteeism studies.
Recruitment/retention (police) | 30000 | 2 | Y | Y | Y | Y | 0 | operating | Avoid 1 police separation every ~3 yrs | U.S. DOJ Office of Justice Programs, 'Calculating the Cost of Police Turnover' (ojp.gov); Orrick (2008): replacing an officer costs ~1–5x annual salary.
Health/wellness avoided costs | 10000 | 2 | Y | Y | Y | N | 0 | general | IAQ, mold, ergonomics | U.S. EPA indoor air quality cost estimates; Harvard T.H. Chan healthy-buildings research (absenteeism, health).
Single-building maint efficiency | 25000 | 2 | Y | N | N | N | 0 | operating | Only Scenario B is single building; C and D operate two | Facilities-management practice: one building vs. two (shared HVAC, roof, systems). Town estimate.
Annual benefit (today's $) |  |  | 380000 | 335000 | 335000 | 115000
ONE-TIME BENEFITS (capital avoidance)
Avoided major capital TH (B) | 2000000
Avoided major capital TH (C and D) | 750000 | [7 empty] | Renovation addresses some, not all
ANNUAL BENEFIT CASH FLOWS
Year |  | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
Scen B: Annual benefit (Yr 3+) |  | 0 | 0 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000
Scen B: Avoided capital (spread Yr 3-30) |  | 0 | 0 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714 | 71428.5714
Scen B: TOTAL ANNUAL BENEFIT |  | 0 | 0 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 451428.5714 | 0
Scen C: Annual benefit (Yr 4+) |  | 0 | 0 | 0 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000
Scen C: Avoided capital (spread Yr 4-30) |  | 0 | 0 | 0 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778 | 27777.7778
Scen C: TOTAL ANNUAL BENEFIT |  | 0 | 0 | 0 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 362777.7778 | 0
Scen D: Annual benefit (Yr 3+) |  | 0 | 0 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000 | 335000
Scen D: Avoided capital (spread Yr 3-30) |  | 0 | 0 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143 | 26785.7143
Scen D: TOTAL ANNUAL BENEFIT |  | 0 | 0 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 361785.7143 | 0
Scen E: Annual benefit (Yr 2+) |  | 0 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000
Scen E: (no avoided TH capital — TH not renovated) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scen E: TOTAL ANNUAL BENEFIT |  | 0 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000 | 115000

## Glossary
Glossary
Plain-language definitions of the terms, methods, and line items used throughout this analysis.
Financial methods
Cost-Benefit Analysis (CBA) | A structured comparison of the full costs and benefits of each option over time, expressed in dollars, so options can be compared on a consistent basis.
Net Present Value (NPV) / Present Value (PV) | Future dollars converted to today's dollars. Because a dollar spent years from now is worth less than a dollar today, future costs are 'discounted' back to the present. PV lets options that spend money in different years be compared fairly.
Discount rate | The yearly rate used to convert future dollars to today's dollars. This analysis uses 4%, close to the Town's cost of borrowing. A higher rate makes future costs look smaller; a lower rate makes them look larger.
Gross Cost (PV) | The present value of an option's total costs over 30 years, before subtracting any benefits. Shown as a negative number because it is a cost.
Net PV | Gross Cost minus the monetized benefits, in present value. The bottom-line cost of an option after accounting for the value it returns. Shown as a negative number.
Nominal vs. real (today's) dollars | Nominal dollars are the actual amounts paid in a future year, including inflation. Real or 'today's' dollars strip inflation out so amounts in different years are comparable.
Inflation rate | The yearly rate at which prices rise. This analysis grows general costs at 2.5% and construction costs at 4%, because construction has risen faster than general prices.
Sensitivity / toggle | A switch in the model that lets a key assumption be turned on or off (for example, the deferred build), so the effect on the result can be tested.
Financing and taxes
Bond | A loan a local government takes out to pay for a large project, repaid with interest over many years (here, 30 years at an assumed 4.5%).
Debt service | The yearly payment of principal and interest on a bond.
Amount bonded | The portion of a project's cost that is financed by issuing a bond, including bond issuance costs.
General Fund tax levy | The total amount of property tax the Town raises each year for its General Fund. The 2026 figure is about $13.33 million.
Taxable value | The total assessed value of property in the Town that can be taxed, after exemptions. About $4.8 billion per the Town Assessor. Used to translate a project's cost into a tax rate.
Median home assessed value | The assessed value of a typical home in the Town, about $332,100. Used to estimate the tax impact on a typical homeowner.
Property tax cap | A New York limit on how much a local government can raise its tax levy each year, generally 2% or inflation, whichever is less, with limited exclusions and a board override option.
If financed using debt finance | A label on the per-resident and tax-impact figures meaning those amounts apply only if the option is paid for by borrowing. Options paid from reserves or grants would differ.
Buildings and program
Square feet per employee (sf/employee) | A planning measure of how much building space each staff member has. The Police Department today has about 205 sf/employee; common planning guidance is 350 to 500.
Space program | The list of rooms and areas a building needs and their sizes, used to estimate how large a building must be.
Renovation vs. addition | Renovation improves existing space. An addition adds new square footage. The VIP study found the Town Hall needs both, because the current footprint cannot fit everything plus an elevator.
Soft costs | Project costs beyond construction itself: design fees, owner's contingency, construction-management and owner's-representative fees, bond issuance, and legal costs.
Construction Manager / Owner's Representative | Professionals hired to manage construction on the Town's behalf and protect the Town's interests on budget, schedule, and quality. Budgeted here at about 3% of construction.
FF&E | Furniture, Fixtures, and Equipment: the movable items needed to make a building usable (desks, workstations, equipment).
Sallyport | An enclosed, secure vehicle bay where police can transfer people in custody safely, out of public view.
Booking | The intake and processing area in a police facility where arrests are recorded.
Facility Condition Assessment (FCA) | An engineering study of a building's systems and their remaining life, used to replace estimated repair costs with engineered figures.
Compliance and risk
ADA (Americans with Disabilities Act) | Federal civil-rights law requiring public buildings to be accessible. Multi-story government buildings generally must provide an accessible route between floors, such as an elevator.
PESH (Public Employee Safety and Health) | New York's workplace-safety program for public employers. Requires a workplace free of recognized hazards and allows fines for failing to fix serious violations.
Cost of inaction | Costs the Town would carry even if it builds nothing, through legal liability, regulatory exposure, lost staff time, and higher insurance. Counted on a risk-weighted basis.
Risk-weighted / expected-value estimate | A reasonable yearly figure for a risk that may or may not occur in a given year, found by weighing the cost of the event by its likelihood.
Deferred build | The assumption in the Do-Minimum option that the Town would still have to build new facilities at the end of 30 years, since doing the minimum delays but does not remove the need.
Asbestos abatement | The controlled removal of asbestos-containing materials before or during construction. Required when older buildings are disturbed; estimated separately because the VIP study excluded it.
The scenarios
Scenario A — Do Minimum | Fix urgent problems, keep renting the police building, keep the existing Town Hall. Includes future repairs and an eventual deferred build.
Scenario B — Full Rebuild | One new combined building for Town Hall, Police, and Court. Sell the old Town Hall and end the police lease.
Scenario C — Split | Build a new Police/Court building and renovate and expand the existing Town Hall.
Scenario D — Purchase | Buy and convert an existing building for Police and Court, and renovate and expand the Town Hall.
Scenario E — Purchase + Do-Minimum Town Hall | Buy and convert a building for Police and Court (like D), but give the Town Hall only base repairs (like A) rather than a full renovation.

## Scenario A - Do Minimum
Scenario A: Do Minimum
Remediate to compliance. Continue police lease. Future capital + deferred build at Yr 30.
SUMMARY METRICS |  | Gross Cost (PV) | Net PV (after benefits) | Year 1 Cost | Amount Bonded | Annual Debt Service
|  | -23698512.4247 | -23698512.4247 | -1164739 | 0 | 0
Line Item | Source | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
ONE-TIME REMEDIATION (Year 1)
Records room water/envelope/mold | Parameters | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical/heater hazard fix | Parameters | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Building security/access control | Parameters | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff restroom access fix | Parameters | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Asbestos abatement premium | Parameters | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADA doorknob retrofit | Parameters | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elevator retrofit | Parameters | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Police compliance (limited; mostly Village) | Parameters | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total one-time remediation |  | 762000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FUTURE CAPITAL REPLACEMENT
Boiler replacement (Yr 5) |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roof replacement (Yr 8) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical service upgrade (Yr 10) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVAC system overhaul (Yr 12) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining window/envelope (Yr 15) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Parking lot resurface (Yr 18) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Boiler replacement #2 (Yr 22) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roof replacement #2 (Yr 28) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0
Subtotal future capital |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 400000 | 0 | 200000 | 0 | 350000 | 0 | 0 | 250000 | 0 | 0 | 150000 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0
DEFERRED BUILD
Deferred building obligation (Yr 30) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47348603.3367
ONGOING OPERATING
Town Hall operating (inflated) |  | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500
Police occupancy |  | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239 | 131239
Subtotal operating |  | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739 | 232739
RISK-WEIGHTED EXPOSURE
Security/workplace violence |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
Restroom PESH |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
Cash transport |  | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Records loss/mold |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
Insurance pressure |  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
Subtotal risk |  | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000
TOTAL ANNUAL NET COST |  | 1164739 | 402739 | 402739 | 402739 | 702739 | 402739 | 402739 | 802739 | 402739 | 602739 | 402739 | 752739 | 402739 | 402739 | 652739 | 402739 | 402739 | 552739 | 402739 | 402739 | 402739 | 752739 | 402739 | 402739 | 402739 | 402739 | 402739 | 852739 | 402739 | 47751342.3367

## Scenario B - Full Rebuild
Scenario B: Full Rebuild (Trophy Point + Land)
Build 50K sqft combined facility. Acquire 7 acres. Sell TH. Terminate police lease.
SUMMARY METRICS |  | Gross Cost (PV) | Net PV (after benefits) | Project Cost | Amount Bonded | Annual Debt Service
|  | -57814686.0196 | -50999189.0099 | -47348603.3367 | 46848603.3367 | 2876108.042
Line Item | Source | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
PROJECT COST BUILD-UP
Land acquisition | 750000
Trophy Point new building | 32677719
Trophy Point storage | 625823
Trophy Point site work | 5268977
Trophy Point FF&E allowance | 1000000
Geothermal alternate (if selected) | 0
Subtotal hard + land | 40322519
A&E / Design fees | 2967938.925
Owner's contingency | 1978625.95
CM/Owner's Rep | 1187175.57
Legal, advisory, permits | 200000
Asbestos (site) | 0
Subtotal pre-bond | 46656259.445
Less: grants | -500000
Bond issuance | 692343.8917
Bonded amount | 46848603.3367
Total project cost | 47348603.3367
ANNUAL CASH FLOW
Debt service |  | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042 | 2876108.042
Existing buildings (during construction) |  | 232739 | 232739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New building operating |  | 0 | 0 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000
Less: TH sale (Yr 3) |  | 0 | 0 | -1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Immediate Yr 1 fixes |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS ANNUAL COST |  | 3168847.042 | 3108847.042 | 2426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042 | 3426108.042
Less: benefits |  | 0 | 0 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | -451428.5714 | 0
NET ANNUAL COST |  | 3168847.042 | 3108847.042 | 1974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 2974679.4705 | 3426108.042

## Scenario C - Split
Scenario C: New PD/Court + VIP Renovation+Addition for TH
Build new PD/Court (~31K sqft). Renovate + add 7,815 sqft to TH per VIP study ($9-12M).
SUMMARY METRICS |  | Gross Cost (PV) | Net PV (after benefits) | Project Cost | Amount Bonded | Annual Debt Service
|  | -54941593.0858 | -49787020.1911 | -44483803.346 | 43983803.346 | 2700233.5504
Line Item | Source | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
NEW POLICE + COURT BUILDING
Land acquisition | 450000
PD+Court hard construction | 22376880
Site work | 3700000
FF&E | 500000
Subtotal new build | 27026880
TOWN HALL RENOVATION + ADDITION (per VIP study)
VIP renovation cost | 4500000
VIP addition cost (7,815 sqft) | 6000000
Asbestos abatement (VIP excludes) | 600000
VIP subtotal (incl. VIP's design+const contingency) | 11100000
A&E/owner's contingency on top of VIP | 1387500
Total TH reno+addition | 12487500
Soft costs on new build (excl. land) | 4319416.4
COMBINED PROJECT COST | 43833796.4
Less: grants | -500000
Bond issuance | 650006.946
Bonded amount | 43983803.346
Total project cost | 44483803.346
ANNUAL CASH FLOW
Debt service |  | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504 | 2700233.5504
TH operating (old, Yrs 1-3) |  | 101500 | 101500 | 101500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Renovated TH operating (Yr 4+, larger building) |  | 0 | 0 | 0 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963
Old police operating (Yrs 1-2) |  | 131239 | 131239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New PD+Court operating (Yr 3+) |  | 0 | 0 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869 | 341869
Two-building overhead (Yr 3+) |  | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000
Less: Rec luncheon revenue |  | 0 | 0 | 0 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000
Immediate Yr 1 fixes |  | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS ANNUAL COST |  | 2992972.5504 | 2932972.5504 | 3178602.5504 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467 | 3204963.5467
Less: benefits |  | 0 | 0 | 0 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | -362777.7778 | 0
NET ANNUAL COST |  | 2992972.5504 | 2932972.5504 | 3178602.5504 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 2842185.769 | 3204963.5467

## Scenario D - Purchase
Scenario D: Purchase PD/Court Building + Renovate+Add TH
Purchase existing ~25K sqft building ($1M placeholder) and convert for PD+Court. Renovate+add TH per VIP. Operate two buildings.
SUMMARY METRICS |  | Gross Cost (PV) | Net PV (after benefits) | Project Cost | Amount Bonded | Annual Debt Service
|  | -28128968.992 | -22666865.7714 | -20802030 | 20302030 | 1246372.9459
Line Item | Source | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
PURCHASE + CONVERT BUILDING
Building purchase price | 1000000
Conversion to police use | 5000000 |  | Holding cells, sallyport, evidence, HVAC, ADA — HIGH UNCERTAINTY
Site work / parking / sallyport | 500000
FF&E | 400000
Subtotal purchase + convert | 6900000
TOWN HALL RENOVATION + ADDITION (per VIP study)
VIP renovation cost | 4500000
VIP addition cost | 6000000
Asbestos abatement | 600000
VIP subtotal | 11100000
A&E/owner's contingency on VIP | 1387500
Total TH reno+addition | 12487500
Soft costs on purchase/convert (excl. purchase) | 1114500
COMBINED PROJECT COST | 20502000
Less: grants | -500000
Bond issuance | 300030
Bonded amount | 20302030
Total project cost | 20802030
ANNUAL CASH FLOW
Debt service |  | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459 | 1246372.9459
TH operating (old, Yrs 1-2) |  | 101500 | 101500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Renovated TH operating (Yr 3+) |  | 0 | 0 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963 | 132860.9963
Old police (Yr 1) |  | 131239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Converted building operating (Yr 2+) |  | 0 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000
Two-building overhead (Yr 2+) |  | 0 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000
Less: Rec luncheon revenue |  | 0 | 0 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000
Immediate Yr 1 fixes |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GROSS ANNUAL COST |  | 1524111.9459 | 1607872.9459 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422 | 1634233.9422
Less: benefits |  | 0 | 0 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | -361785.7143 | 0
NET ANNUAL COST |  | 1524111.9459 | 1607872.9459 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1272448.2279 | 1634233.9422

## Scenario E - Purchase+DoMin TH
Scenario E: Purchase PD/Court Building + Do-Minimum Town Hall
Purchase & convert a ~25K sqft building for Police/Court (like Scenario D), but the Town Hall receives only base remediation and the ongoing capital-replacement schedule (like Scenario A) — no full VIP renovation/addition.
SUMMARY METRICS |  | Gross Cost (PV) | Net PV (after benefits) | Project Cost | Amount Bonded | Annual Debt Service
|  | -22490992.0942 | -20612985.1877 | -8127217.5 | 7627217.5 | 468246.6504
Line Item | Source | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
PURCHASE + CONVERT BUILDING
Building purchase price | 1000000
Conversion to police use | 5000000 |  | Holding cells, sallyport, evidence, HVAC, ADA — HIGH UNCERTAINTY
Site work / parking / sallyport | 500000
FF&E | 400000
Subtotal purchase + convert | 6900000
TOWN HALL — BASE REMEDIATION (one-time, Year 1)
Records room water/envelope/mold | 90000
Electrical/heater hazard fix | 30000
Building security/access control | 30000
Staff restroom access fix | 60000
ADA doorknob retrofit | 10000
Elevator retrofit | 450000
Subtotal TH base remediation (incl. asbestos premium) | 804000
Soft costs on purchase/convert (excl. purchase) | 1114500
COMBINED PROJECT COST | 8014500
Less: grants | -500000
Bond issuance | 112717.5
Bonded amount | 7627217.5
Total project cost | 8127217.5
ANNUAL CASH FLOW
Debt service |  | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504 | 468246.6504
Deferred Town Hall build (Yr 30) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500000
TH operating (do-minimum, all years) |  | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500 | 101500
Converted building operating (Yr 2+) |  | 0 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000
Two-building overhead (Yr 2+) |  | 0 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000
Old police lease (Yr 1) |  | 131239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TH base remediation (one-time, Yr 1) |  | 804000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Future capital replacement (TH) |  | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 400000 | 0 | 200000 | 0 | 350000 | 0 | 0 | 250000 | 0 | 0 | 150000 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 0
Risk-weighted exposure (continues) |  | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000
Less: Rec luncheon revenue |  | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000
GROSS ANNUAL COST |  | 1669985.6504 | 994746.6504 | 994746.6504 | 994746.6504 | 1294746.6504 | 994746.6504 | 994746.6504 | 1394746.6504 | 994746.6504 | 1194746.6504 | 994746.6504 | 1344746.6504 | 994746.6504 | 994746.6504 | 1244746.6504 | 994746.6504 | 994746.6504 | 1144746.6504 | 994746.6504 | 994746.6504 | 994746.6504 | 1344746.6504 | 994746.6504 | 994746.6504 | 994746.6504 | 994746.6504 | 994746.6504 | 1444746.6504 | 994746.6504 | 11494746.6504
Less: benefits |  | 0 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000 | -115000
NET ANNUAL COST |  | 1669985.6504 | 879746.6504 | 879746.6504 | 879746.6504 | 1179746.6504 | 879746.6504 | 879746.6504 | 1279746.6504 | 879746.6504 | 1079746.6504 | 879746.6504 | 1229746.6504 | 879746.6504 | 879746.6504 | 1129746.6504 | 879746.6504 | 879746.6504 | 1029746.6504 | 879746.6504 | 879746.6504 | 879746.6504 | 1229746.6504 | 879746.6504 | 879746.6504 | 879746.6504 | 879746.6504 | 879746.6504 | 1329746.6504 | 879746.6504 | 11379746.6504